# SpendWise – Personal Expense Tracker API

Agile & DevOps Capstone Project Documentation

February 2026

# Project Workflow Diagrams

Figure 1: Overall Project Flow Diagram

Figure 2: Project Timeline

# Sprint 0: Planning (Setup)

## Product Vision

SpendWise is a REST API that lets users register an account, track income and expenses by category, and view spending summaries, giving people a simple tool to understand where their money goes.

## Product Backlog

The Product Backlog contains all user stories for the SpendWise API. Each story includes acceptance criteria, story points, and priority.

### US-01: Register an Account

As a new user, I want to create an account with my name, email, and password, so that I can start tracking my expenses.

Acceptance Criteria:

POST /api/auth/register accepts { name, email, password }

Password is hashed with bcrypt before storing (never stored in plain text)

Returns 201 Created with { id, name, email, created_at } (no password in response)

Returns 400 if name, email, or password is missing

Returns 400 if email format is invalid

Returns 409 Conflict if email is already registered

Password must be at least 6 characters

Story Points: 3  |  Priority: P0 (Critical)

### US-02: Log In

As a registered user, I want to log in with my email and password, so that I can access my data.

Acceptance Criteria:

POST /api/auth/login accepts { email, password }

Compares password against bcrypt hash

Returns 200 OK with { token } (JWT valid for 24h)

Returns 401 Unauthorized if email doesn't exist or password is wrong

The JWT payload contains { userId, email }

Story Points: 3  |  Priority: P0 (Critical)

### US-03: Add a Transaction

As a logged-in user, I want to record an income or expense with an amount, category, and date, so that I can track where my money goes.

Acceptance Criteria:

POST /api/transactions accepts { type, amount, category, description?, date? }

Requires a valid JWT in Authorization: Bearer <token> header

type must be either "income" or "expense"

amount must be a positive number

category is required (e.g., "food", "salary", "transport")

date defaults to today if not provided

Returns 201 Created with the saved transaction

Returns 401 if no token or invalid token

Returns 400 if required fields are missing or invalid

Story Points: 3  |  Priority: P0 (Critical)

### US-04: List My Transactions

As a logged-in user, I want to see all my transactions sorted by date, so that I can review my financial activity.

Acceptance Criteria:

GET /api/transactions returns only the authenticated user's transactions

Sorted by date descending (most recent first)

Each transaction includes id, type, amount, category, description, date

Returns 200 OK with empty array if the user has no transactions

Returns 401 if not authenticated

Story Points: 2  |  Priority: P1 (High)

### US-05: Filter Transactions

As a logged-in user, I want to filter my transactions by type, category, or date range, so that I can find specific entries quickly.

Acceptance Criteria:

GET /api/transactions?type=expense filters by income or expense

GET /api/transactions?category=food filters by category (case-insensitive)

GET /api/transactions?from=2026-01-01&to=2026-01-31 filters by date range

Filters can be combined: ?type=expense&category=food

Returns 200 OK with matching transactions or empty array

Returns 401 if not authenticated

Story Points: 3  |  Priority: P1 (High)

### US-06: Get Spending Summary

As a logged-in user, I want to see my total income, total expenses, and balance, broken down by category, so that I understand my spending patterns.

Acceptance Criteria:

GET /api/transactions/summary returns total_income, total_expenses, balance, by_category

Only computes data for the authenticated user

Accepts optional ?from= and ?to= date range

Returns zeroed values if user has no transactions

Returns 401 if not authenticated

Story Points: 3  |  Priority: P2 (Medium)

### US-07: Health Endpoint

As a DevOps engineer, I want a health endpoint that checks the API and database status, so that I can monitor the service.

Acceptance Criteria:

GET /health returns 200 OK when healthy with status, uptime, timestamp, database, version

Actually runs SELECT 1 against Postgres to verify DB connectivity

Returns 503 Service Unavailable with "database": "disconnected" if DB is down

Does NOT require authentication

Story Points: 2  |  Priority: P1 (High)

### Backlog Summary

| ID | Story | Points | Priority |
| --- | --- | --- | --- |
| US-01 | Register an Account | 3 | P0 (Critical) |
| US-02 | Log In | 3 | P0 (Critical) |
| US-03 | Add a Transaction | 3 | P0 (Critical) |
| US-04 | List My Transactions | 2 | P1 (High) |
| US-05 | Filter Transactions | 3 | P1 (High) |
| US-06 | Spending Summary | 3 | P2 (Medium) |
| US-07 | Health Endpoint | 2 | P1 (High) |

Total Story Points: 19

### Estimation Method

Story points are assigned using Fibonacci sequence (1, 2, 3, 5, 8, 13). Estimation factors include complexity, amount of new code, testing effort, and integration with existing components.

## Definition of Done (DoD)

### Code Quality

Code compiles/builds without errors

Code follows project style guidelines (ESLint passes with no errors)

No console.log or debugger statements left in production code

Meaningful variable and function names

Functions are small and do one thing well (Single Responsibility Principle)

### Testing

All acceptance criteria have corresponding test cases

Unit tests pass (≥ 80% code coverage for new code)

Integration tests pass

All tests pass in CI pipeline before merge

### Documentation

Code is self-documenting with clear comments where necessary

API endpoints are documented (method, path, request/response format)

README is updated with setup instructions

Environment variables are documented in .env.example

### Version Control

Feature branches are used (no direct commits to main/dev)

Commit messages are descriptive and follow conventional commit format

Pull requests have clear descriptions linking to user stories

No “big-bang” commits – work is broken into logical, incremental commits

### Security

No secrets or credentials committed to version control

Passwords are hashed (bcrypt) before storage

JWT secrets are environment variables, not hardcoded

SQL injection is prevented (parameterized queries)

Input validation is implemented on all endpoints

### DevOps

Docker image builds successfully

CI pipeline runs successfully on all branches

Tests run automatically on every pull request

Health endpoint is implemented and working

Application runs successfully with docker-compose up

## Sprint 1 Plan

Sprint Goal: Deliver core authentication and transaction creation functionality.

| Story | Points | Priority |
| --- | --- | --- |
| US-01: Register an Account | 3 | P0 |
| US-02: Log In | 3 | P0 |
| US-03: Add a Transaction | 3 | P0 |

Total commitment: 9 story points

### Sprint 1 Dependencies

US-02 depends on US-01 (need users table for login)

US-03 depends on US-02 (need JWT middleware for authentication)

## Sprint 2 Plan

Sprint Goal: Deliver transaction listing, filtering, summary, and health monitoring.

| Story | Points | Priority |
| --- | --- | --- |
| US-04: List My Transactions | 2 | P1 |
| US-05: Filter Transactions | 3 | P1 |
| US-06: Get Spending Summary | 3 | P2 |
| US-07: Health Endpoint | 2 | P1 |

Total commitment: 10 story points

## Sprint 0 Summary

| Goal | Status |
| --- | --- |
| Define a Product Vision | Complete |
| Create a Product Backlog (7 user stories) | Complete |
| Refine the Backlog (acceptance criteria, priorities, estimates) | Complete |
| Establish Standards (Definition of Done) | Complete |
| Plan Sprint 1 (3 stories, 9 points) | Complete |
| Plan Sprint 2 (4 stories, 10 points) | Complete |

# Sprint 1: Execution

## Environment Setup

Figure 3: PostgreSQL running in Docker

Figure 4: Application logs in Docker

Figure 5: Database schema verification

## Delivered Work

| User Story | Feature | Points | Status |
| --- | --- | --- | --- |
| US-01 | Register an Account | 3 | Complete |
| US-02 | Log In | 3 | Complete |
| US-03 | Add a Transaction | 3 | Complete |

### US-01: Register an Account

Features Delivered:

POST /api/auth/register endpoint

Password hashing with bcrypt

Email validation and duplicate checking

Returns 201 with user data (no password)

### US-02: Log In

Features Delivered:

POST /api/auth/login endpoint

JWT token generation (24h expiry)

Password comparison with bcrypt

Returns 200 with JWT token

### US-03: Add a Transaction

Features Delivered:

POST /api/transactions endpoint

JWT authentication required

Transaction validation (type, amount, category)

Date defaults to today

## Version Control (Git)

Commit history showing iterative, incremental delivery:

851f4a9 feat: add project configuration and Docker setup
742e6b5 feat: implement Express.js API structure and core components
0763e52 ci: set up CI/CD pipeline, tests, and linting
f21831b test: add comprehensive test suites for Sprint 1
bb3c257 fix: resolve test and lint issues

Git Branch Strategy:

master (production)
  └── dev (integration)
       ├── feature/sprint-1-authentication
       └── feature/sprint-2-transactions

## CI/CD Pipeline Setup

GitHub Actions CI/CD pipeline configured in .github/workflows/ci.yml. Runs on every push and pull request.

| Stage | Description | Status |
| --- | --- | --- |
| 1 | Checkout code | Passed |
| 2 | Build Docker image | Passed |
| 3 | Setup Node.js 20 | Passed |
| 4 | Install dependencies | Passed |
| 5 | Run ESLint | Passed |
| 6 | Run Jest tests | Passed |
| 7 | Deploy to Render (master only) | Configured |

Pipeline Configuration (ci.yml):

name: CI/CD Pipeline
on:
  push:
    branches: ["*"]
  pull_request:
    branches: [master, dev]

jobs:
  build-and-test:
    runs-on: ubuntu-latest
    services:
      postgres:
        image: postgres:16-alpine
    steps:
      - Checkout code
      - Build Docker image
      - Setup Node.js 20
      - Install dependencies (npm ci)
      - Run ESLint
      - Run tests (npm test)

  deploy:
    needs: build-and-test
    if: github.ref == 'refs/heads/master'
    steps:
      - Trigger Render deploy hook

## Testing (Sprint 1)

| Metric | Value |
| --- | --- |
| Test Suites | 5 |
| Total Tests | 27 |
| Passing | 27 |
| Failing | 0 |
| Pass Rate | 100% |
| Code Coverage | 64.25% |

### Acceptance Criteria Coverage

| User Story | Total ACs | Tested | Coverage |
| --- | --- | --- | --- |
| US-01 | 9 | 9 | 100% |
| US-02 | 7 | 7 | 100% |
| US-03 | 9 | 9 | 100% |
| Total | 25 | 25 | 100% |

### Sprint 1 Test Screenshots

Figure 6: Registration tests passed

Figure 7: Login tests passed

Figure 8: Authentication tests passed

Figure 9: Transaction tests passed

### Sprint 1 API Testing Screenshots

Figure 10: Registration success

Figure 11: Missing email validation

Figure 12: Invalid email – 401

Figure 13: Login success

Figure 14: Transaction creation success

Figure 15: No token – 401

Figure 16: Invalid token – 401

Figure 17: Negative amount validation

## Sprint 1 Review

Sprint 1 successfully delivered all 3 planned user stories (9 story points) with a fully functional authentication system, transaction creation capability, 27 passing tests (64% coverage), CI/CD pipeline configured, and Docker support.

### Technical Foundation Established

| Component | Status |
| --- | --- |
| Express.js API | RESTful structure |
| PostgreSQL Database | Users & transactions tables |
| Authentication (JWT) | bcrypt + jsonwebtoken |
| Input Validation | express-validator |
| Logging | Winston + Morgan |
| Docker Support | Dockerfile + docker-compose |
| CI/CD Pipeline | GitHub Actions |

### Sprint 1 Burndown

| Day | Points Completed | Cumulative |
| --- | --- | --- |
| Day 1 | 3 (US-01) | 3 |
| Day 2 | 3 (US-02) | 6 |
| Day 3 | 3 (US-03) | 9 |
| Day 4+ | Testing & Documentation | 9 |

## Sprint 1 Retrospective

### What Went Well

Iterative Commit History – Small, incremental commits throughout development with clear messages.

Test-Driven Development – Wrote tests during implementation; achieved 100% pass rate.

Complete Documentation – Comprehensive test execution report, acceptance criteria mapped.

Docker Containerization – Local dev environment ready with single command.

### What Could Be Improved

Test Database Setup – Initial test runs failed due to database connection pooling conflicts. Fix: use --runInBand flag.

Environment Configuration – DATABASE_URL not read properly in initial test runs. Fix: explicitly create .env before tests.

Date Handling – PostgreSQL returning different date format. Fix: standardize ISO 8601 format.

### Action Items for Sprint 2

| Priority | Action | Status |
| --- | --- | --- |
| P1 (High) | Use --runInBand flag for test execution | Applied |
| P1 (High) | Create .env file with DATABASE_URL | Applied |
| P2 (Medium) | Standardize date format in responses | Applied |
| P2 (Medium) | Increase code coverage to >80% | Achieved (90.63%) |

### Process Metrics (Sprint 1)

| Metric | Value |
| --- | --- |
| Story Points Completed | 9/9 (100%) |
| Tests Written | 27 |
| Test Pass Rate | 100% |
| Code Coverage | 64.25% |
| Commits | 5 |
| Bugs Found/Fixed | 3/3 |

# Sprint 2: Execution & Improvement

## Feedback Applied from Sprint 1 Retrospective

| Improvement | Applied? | Result |
| --- | --- | --- |
| Use --runInBand flag | Yes | Tests run sequentially, no conflicts |
| Create .env file | Yes | DATABASE_URL properly set |
| Standardize date handling | Yes | Consistent date formats in responses |
| Increase coverage | Yes | Improved from 64% to 90.63% |

## Delivered Work

| User Story | Feature | Points | Status |
| --- | --- | --- | --- |
| US-04 | List My Transactions | 2 | Complete |
| US-05 | Filter Transactions | 3 | Complete |
| US-06 | Get Spending Summary | 3 | Complete |
| US-07 | Health Endpoint | 2 | Complete |

### US-04: List My Transactions

Features Delivered:

GET /api/transactions endpoint

Returns only authenticated user's transactions

Sorted by date descending (most recent first)

Returns empty array if no transactions

### US-05: Filter Transactions

Features Delivered:

Filter by type: ?type=income|expense

Filter by category: ?category=food (case-insensitive)

Filter by date range: ?from=YYYY-MM-DD&to=YYYY-MM-DD

Combined filters supported

### US-06: Get Spending Summary

Features Delivered:

GET /api/transactions/summary endpoint

Returns: total_income, total_expenses, balance

Category breakdown in by_category object

Optional date range filtering; zero values for new users

### US-07: Health Endpoint

Features Delivered:

GET /health endpoint (public, no authentication)

Returns: status, uptime_seconds, timestamp, database, version

Database connectivity check (SELECT 1)

Returns 503 if database is disconnected

## Monitoring & Logging

Winston logger for application logs

Morgan middleware for HTTP request logs

Health endpoint with database connectivity check

Error logging in all controllers

Request/response logging in CI/CD

Log Output Example:

info: User registered successfully: john@example.com
  {"service":"spendwise-api","timestamp":"2026-02-10T13:23:20.708Z"}
info: ::ffff:127.0.0.1 "POST /api/transactions HTTP/1.1" 201 168

## Testing (Sprint 2)

| Metric | Sprint 1 | Sprint 2 | Improvement |
| --- | --- | --- | --- |
| Test Suites | 4 | 7 | +3 |
| Total Tests | 27 | 45 | +18 |
| Pass Rate | 100% | 100% | Same |
| Code Coverage | 64.25% | 90.63% | +26.38% |

### Coverage by Module

| Module | Statements | Branches | Functions | Lines |
| --- | --- | --- | --- | --- |
| All files | 90.63% | 81.48% | 81.81% | 90.63% |
| Controllers | 81.33% | 75% | 100% | 81.33% |
| Middleware | 92.3% | 87.5% | 100% | 92.3% |
| Models | 97.22% | 91.66% | 85.71% | 97.22% |
| Routes | 100% | 100% | 100% | 100% |

### Acceptance Criteria Coverage (All Sprints)

| User Story | Total ACs | Tested ACs | Coverage |
| --- | --- | --- | --- |
| US-01 | 9 | 9 | 100% |
| US-02 | 7 | 7 | 100% |
| US-03 | 9 | 9 | 100% |
| US-04 | 4 | 4 | 100% |
| US-05 | 5 | 5 | 100% |
| US-06 | 5 | 5 | 100% |
| US-07 | 4 | 4 | 100% |
| Total | 43 | 43 | 100% |

### Sprint 2 Test Screenshots

Figure 18: Health tests passed

Figure 19: Transaction list tests passed

Figure 20: Summary tests passed (90% coverage)

### Sprint 2 API Testing Screenshots

Figure 21: List transactions

Figure 22: Filter by type

Figure 23: Filter by category

Figure 24: Filter by date range

Figure 25: Combined filters

Figure 26: Summary endpoint

Figure 27: Health endpoint

## Sprint 2 Review

Sprint 2 successfully delivered all 4 planned user stories (10 story points) with significant improvements: 90.63% code coverage (up from 64.25%), 45 tests passing (up from 27), full monitoring (health endpoint + logging), and all acceptance criteria tested.

### Sprint 2 Burndown

| Day | Points Completed | Cumulative |
| --- | --- | --- |
| Day 1 | 5 (US-04, US-05 tests) | 5 |
| Day 2 | 5 (US-06, US-07 tests) | 10 |
| Day 3 | Documentation & Review | 10 |

### Definition of Done Status

| Criterion | Sprint 1 | Sprint 2 |
| --- | --- | --- |
| Code follows style guidelines | Pass | Pass |
| Tests pass | 100% | 100% |
| Code merged to dev | Done | Done |
| CI pipeline passes | Pass | Pass |
| Documentation updated | Done | Done |
| Code coverage > 80% | 64% (below) | 90.6% (above) |

## Final Retrospective

### Sprint-by-Sprint Comparison

| Metric | Sprint 1 | Sprint 2 | Improvement |
| --- | --- | --- | --- |
| Story Points | 9 | 10 | +1 |
| Tests | 27 | 45 | +18 |
| Coverage | 64.25% | 90.63% | +26.38% |
| Pass Rate | 100% | 100% | Same |
| User Stories | 3 | 4 | +1 |

### Lessons Learned

Technical Lessons:

Docker First Approach – Starting with Docker simplifies environment setup. CI/CD integrates naturally.

Test-Driven Development – Writing tests during implementation catches bugs early. 100% pass rate maintained.

CI/CD is Non-Negotiable – Automated testing catches issues immediately. Quality gates keep code clean.

Git Flow Discipline – Feature branches enable parallel work. Merge to dev keeps master clean.

Agile Lessons:

Sprint Planning Matters – Well-defined acceptance criteria = successful delivery.

Retrospectives Drive Improvement – Identified specific, actionable improvements and applied all 3.

Definition of Done Enforces Quality – Clear DoD prevented cutting corners.

### What I Would Do Differently

Start CI/CD earlier – Set up pipeline skeleton in Sprint 0 before writing code.

More detailed acceptance criteria – Add edge cases and boundary conditions to ACs.

Separate test database – Use test containers for true isolation from the start.

Plan pagination earlier – Even if not required for MVP, saves refactoring later.

### Skills Developed

| Skill | Before | After |
| --- | --- | --- |
| Node.js/Express | Basic | Proficient |
| PostgreSQL | Basic | Intermediate |
| Docker | Basic | Intermediate |
| Git/GitHub | Basic | Proficient |
| CI/CD (GitHub Actions) | None | Proficient |
| Jest Testing | Basic | Proficient |
| Agile Practices | Theoretical | Practical |

# CI/CD Pipeline Evidence

## CI/CD Screenshots

Figure 28: First CI/CD test on master failed

Figure 29: After fixing DB error – all CI/CD tests passed

Figure 30: Deployment configuration in Docker

Figure 31: Render deploy hook added to GitHub Actions secrets

Figure 32: Retrieving Render deploy hooks

Figure 33: Disabled Render auto-deploy (CI/CD handles deployment)

Figure 34: Successful deployment on GitHub Actions

Figure 35: Tables migrated successfully to remote DB

## Secrets Configuration

| Secret | Purpose | Status |
| --- | --- | --- |
| DATABASE_URL | Production database connection | Configured |
| JWT_SECRET | JWT signing key | Configured |
| RENDER_DEPLOY_HOOK_URL | Auto-deploy trigger | Configured |

# Final Project Completion Summary

| Metric | Value |
| --- | --- |
| Total User Stories | 7 |
| Total Story Points | 19 |
| Completed Stories | 7 (100%) |
| Completed Points | 19 (100%) |
| Total Test Cases | 45 |
| Passing Tests | 45 (100%) |
| Code Coverage | 90.63% |
| CI/CD Pipeline | Configured & Passing |
| Docker Support | Configured |

## API Endpoints

| Method | Endpoint | Description | Status |
| --- | --- | --- | --- |
| POST | /api/auth/register | Register new user | Complete |
| POST | /api/auth/login | Login, get JWT | Complete |
| POST | /api/transactions | Create transaction | Complete |
| GET | /api/transactions | List user's transactions | Complete |
| GET | /api/transactions?filters | Filter transactions | Complete |
| GET | /api/transactions/summary | Get spending summary | Complete |
| GET | /health | Health check | Complete |

The SpendWise Personal Expense Tracker API has been successfully implemented following Agile and DevOps best practices. All 7 user stories completed (19 story points), 45 tests passing with 90.63% coverage, fully functional CI/CD pipeline, and comprehensive documentation provided.